## Defects
Sl No | Submitted By | Submitted Date | Description | Detected Sprint | Assigned To | Type Of Defect | Action Taken | Action Taken Date | Status(Open/Closed) | Remarks
1 | Anuj Khedikar | 2026-03-02 | In the code editor section the detail insights were not been given by AI model. | Sprint 1 | Self | Standards | In the backend the prompt section which will be calling the model via API, is changed from simple to in detailed prompting. | 2026-03-02 | Closed | Issue has been resolved and also the user is able to see the in-detail insights of the pasted code in the editor.
2 | Anuj Khedikar | 2026-03-06 | Backend error. I was getting a 502: Server Error when I clicked on the "Analyze Code" button. | Sprint 2 | Self | Standards | In the backend app.py file the particular code related specification was missing, and I detected it and added the requirements to resolve the backend issue. | 2026-03-06 | Closed | The backend issue is resolved and also now the system is working perfectly fine, so now when user clicks on the "Analyze Code" button, it is giving the in-detail insights.
3 | Anuj Khedikar | 2026-03-09 | Language mis-match issue. | Sprint 3 | Self | Standards | When the user selects a langauge and gives a different code in the editor, the AI was not able to detect the language mis-match, so a proper code settings and along with the access to the dropdown of the language was given to AI to check if the choosen language and the pasted code in editor perfectly matches the syntax respectively. | 2026-03-20 | Closed | The language mis-match issue has been resolved and also now the AI detects the issue and provides the "Language Mis-Match" warning, along side a detailed explanation regarding the same.
4 | Anuj Khedikar | 2026-03-16 | Tracking the previous code by AI Agent. | Sprint 4 | Self | Standards | The previous code was not been tracked by the AI Agent, so the previous code of a particular choosen language will be remembered by the AI and provides the response. | 2026-03-20 | Closed | The issue has been resolved, now the AI Agent tracks the even the previous code and responds accordingly.

## Sheet2
Logical
User Interface
Maintainability
Standards
Others